## IRONMAN 70.3
IRONMAN ¦ 5150 Paraguay — El Delta Nueva Asunción · 25 April 2027 |  | There are many elements of event production that need careful consideration when determining if a new event will be viable. The following provides a summary of key considerations that a licensee should review and submit comment on prior to requesting the establishment of a new event. The below document has been retained as per the original (shared by IRONMAN ) questionnarie with no changes to the questions, order of questions or topics with only formatted and presented differently for better trackability of responses.
< | # | Question | Assessment and Response
Cost /Revenue /Benefits | 1 | Comment on 5 potential ‘major’ cost areas (i.e., Traffic Control personnel/Equipment, Police, Banquets/Food, Personnel, Travel/Housing and/or Venue Fees). Areas of major cost concern based on venue, location, etc.? | IM License Fee (5150 tier), Maintenance Fees and IM team Expenses, Personnel, Signage/Display Equipment, Site & Expo Equipment, Athletes Kit. Finish Line, VIP hospitality.
| 2 | Comment on other expenses that are difficult to estimate and what the factors are that will affect them. | Athletes registration drives the venue change to Asunción. Encarnación attendance constrained by connectivity. Capital-city positioning + Silvio Pettirossi international airport unlock materially higher registration. The 5150 specifically is positioned as season-opener for the Southern Cone triathlon calendar and as the natural build-up race for the IRONMAN 70.3 Paraguay 2027 — 17 weeks of training window between events. Year 1 target: 800-1,000 atletas, with trajectory toward 1,500 cap by Year 3 in this venue.
| 3 | What is the financial commitment from local partners? Length of commitment? | Strong multi-year commitment under negotiation with El Delta Nueva Asunción as Official Venue + Official Sponsor for 2027/2028 with option for 2029. Title sponsor ueno bank should be renovated. Marca País Paraguay endorsement granted at the national level, providing institutional continuity across editions.
| 4 | Ability to secure sponsorship? Attractiveness to existing partners? | Substantially improved. Asunción concentrates the majority of Paraguay's corporate HQs (in addition to ueno bank, Tigo, Personal, Claro, Cervepar, Grupo Vierci, Grupo Zuccolillo, among others). The El Delta venue partnership additionally unlocks the premium real estate sector as an active sponsor category — not previously addressable from Encarnación.
| 5 | How necessary to the success of the event is outside support? | More accessible. Government support is structured through the Marca País Paraguay endorsement (national) plus Municipalidad de Asunción (city). Financial support from sponsors expected materially higher than the Encarnación cycle.
Swim | 1 | River, Lake or Ocean swim? | River (Río Paraguay) at the El Delta Nueva Asunción venue — same venue as the IRONMAN 70.3 Paraguay 2027 (August edition). 5150 swim distance: 1.5km. Final swim segment placement TBC pending venue master plan.
| 2 | Depth of body of water, water temperature at the time of year event is planned? | Río Paraguay near Asunción in late April (Southern Hemisphere autumn): water temperature typically 22-24°C. Final swim segment depth TBC pending site survey. Wetsuit-legal status to be confirmed against IRONMAN cutoff (typical 24.5°C threshold).
| 3 | One lap or multi-lap? | Point to Point (one direction) — 1.5km olympic-distance swim.
| 4 | Comment on current, tidal or other water issues. Does wind create a factor? | The Paraguay River near Asunción is generally calm in morning hours. April is a stable autumn-transition month — occasional frontal weather events possible but typically mild. For this specific swim course, the format would be point-to-point, from Point A to Point B, with the natural current expected to be in favor of the athletes. This creates a swim dynamic similar in concept to other well-known downstream or current-assisted race venues, such as Panama or Chattanooga. Final wind/current assessment TBC.
| 5 | Any significant weather occurrences to be concerned about (typhoon, hurricanes, significant thunderstorms or rain, or other) that could impact swim? Is the course protected (break wall, boat harbor, other)? | Late April in Asunción (Southern Hemisphere autumn transition): low rainfall risk (~80mm monthly avg, declining toward end of April), no significant meteorological phenomena recorded historically. Stable autumn river conditions. Final break-wall/harbor configuration TBC.
| 6 | Access to trained water safety and/or support staff in the area as needed? Where are the extraction points for critical injuries and are they away from crowds or easily accessible? | Coordination with Prefectura Naval (national HQ in Asunción). Trained rescue teams + medical team at entry/exit. 5150 swim shorter (1.5km) — tighter rescue coverage requirements than 70.3.
| 7 | If a boating/shipping area, is there the ability to shut down any water traffic as needed. | The Río Paraguay at Asunción has commercial river traffic that can be managed via Prefectura Naval (national HQ jurisdiction). Specific traffic shutdown protocol TBC pending final swim location.
| 8 | Clean access (entrance/exit) to/from the swim area. Ability to access water for equipment set up? | Yes — clean access for both entry and exit will be designed jointly with the El Delta venue site team. Final layout TBC.
| 9 | Comment on distance from transition zone. | Target: less than 100m from swim-out to transition zone — same proven IRONMAN standard. Final distance TBC pending venue master plan.
| 10 | Any other restrictions or concerns in relation to swim? | No significant restrictions identified. The El Delta venue partnership provides controlled premium development infrastructure. Prefectura Naval central HQ enables strong institutional support.
Bike | 1 | How many laps is the course? One, two or more? Is it a looped course or does it feature out and back sections? Any oddities to proposed course design? | 2 laps of 20km, out-and-back design within and around the El Delta Nueva Asunción venue. Flat, fast circuit — key strategic advantage of the venue. Total bike distance: 40km (5150 standard). Shares core route corridor with the 70.3 for operational efficiency. Final route design TBC.
| 2 | Road quality. What is the pavement like? Road width? Wide lanes with shoulder or narrow roads? | Roads in the Asunción metropolitan area connecting to El Delta have excellent asphalt quality. The El Delta development itself is built with premium-standard road infrastructure. Both lanes of the cycling course will be closed for the event.
| 3 | How much climbing is included on proposed course? | Significantly lower elevation gain than Encarnación, and proportionally less than the 70.3 given the shorter distance. Preliminary target ≤74m total over both laps.
| 4 | Road Closures - Ability to fully close roads or partial closures? If partial closures what is traffic control plan? Can cars and bikes be safely separated and controlled? | Full closures planned with coordination of Policía Nacional, ANT (Agencia Nacional de Tránsito), Municipalidad de Asunción and Marca País Paraguay. The El Delta venue itself is a controlled premium development zone — internal circuit closures are operationally simpler than open-city closures.
| 5 | Any crossovers, bike to bike or bike and vehicle? | No crossovers planned. Final design TBC.
| 6 | Comment on access for aid stations? | Two aid stations planned at the turnaround point of the bike circuit. Given the 40km looped design, the stations are well-positioned to serve athletes on both laps.
| 7 | Comment on parking for volunteers - wide, safe locations? | El Delta venue includes dedicated parking infrastructure. Specific volunteer parking allocation TBC pending venue master plan.
| 8 | Any ‘bad’ sections that need special attention, steep hills, bad curves, bad or narrow road sections, train tracks, etc.? | No significant 'bad' sections expected in preliminary review — the venue change strategically targets a flatter, faster, safer profile. Specific attention points TBC pending route finalization.
| 9 | What is potential traffic/community impact of bike course? Can ‘local access’ be provided to impacted residents? Any community issues (i.e. cutting off churches, hospitals, etc.)? | Bike route segments outside the El Delta venue will require coordination with Municipalidad de Asunción, Police and MOPC and potentially neighboring municipalities. Specific route + alternative access plan TBC.
| 10 | What is the access to/for Emergency Management Services? How close are hospitals to course? | Asunción metropolitan area has the most extensive hospital network in Paraguay: Hospital Central IPS, Hospital de Clínicas (UNA), Hospital del Trauma, Sanatorio Italiano, Sanatorio San Roque, plus multiple specialized private centers. One ambulance per turnaround point planned.
| 11 | Does the course have the support of all the jurisdictions (city, county, state, provincial, police)? Can the course be managed safely? | Full institutional support structure: Marca País Paraguay (national endorsement), Municipalidad de Asunción (city), Policía Nacional + ANT (traffic), Prefectura Naval (river). Coordination protocol being established as part of this venue change application.
1
Run | 2 | How many laps is the course? One, two or more? Is it a looped course or does it feature out and back sections? Any oddities to proposed course design? | Proposed: 2 laps of 5km + segment to finish line. Flat profile within/around the El Delta venue. 10km Olympic-distance format. Final design TBC.
| 3 | Road Quality - What is the pavement or trail quality like? Road or trail width? Any off-road or trail running? | El Delta venue premium development infrastructure — paved roads and pedestrian pathways in excellent condition. Specific run surface segment TBC pending venue master plan.
| 4 | How much climbing is included on the proposed course? | Minimal elevation gain expected. Target ≤40m total over the 10km — flat-and-fast profile.
| 5 | Road Closures – Ability to fully close roads or partial closures? If partial closures what is traffic control plan? Can cars and runners (if applicable) be safely separated and controlled? | Full closure of run course routes. Internal venue pedestrian paths are controlled by El Delta development. External segments coordinated with Municipalidad and Policía Nacional.
| 6 | Any crossovers, runner to bike, runner to runner, etc.? | No crossovers planned. Final design TBC.
| 7 | Access for Aid Stations? Parking for volunteers, wide, safe locations? | Two hydration stations planned (midpoint and turnaround across both 5km laps). Volunteer/crew parking integrated with main event area at El Delta.
| 8 | Any ‘bad’ sections that need special attention, particularly in relation to traffic? | No specific high-risk sections identified at preliminary review. Final assessment TBC.
| 9 | What is potential traffic/community impact of run course? Can ‘local’ access be provided to residents? Any community issues, i.e. cutting off churches, hospitals, etc. | Run course within the El Delta venue is a private master-planned development with controlled access — minimal external community impact.
| 10 | Comment on access to/for Emergency Management Services. How close are hospitals to course?Ambulance or ATV access to move athletes? | One ambulance per turn point. Direct access to Asunción hospital network (Hospital Central IPS, Sanatorio de la Costa - Hospital del Trauma, Sanatorio Italiano, multiple private centers).
| 11 | Does the course have the support of all the jurisdictions (city, county, state, provincial, police)? Can the course be managed safely? | Full institutional support: SENATUR - Marca País Paraguay + Municipalidad de Asunción + Policía Nacional + MOPC.
Transition | 1 | Is the event single or multi-transition? If multi, how far apart are locations? Is a single transition option available? | Double transition area, target <100m from swim start. 5150 footprint materially more compact than the 70.3 (~1/3 of bike volume). Final layout TBC.
| 2 | How much space is available for transitions? Does everything needed fit? Is it a space that is merely functional or is it a space that can be flushed out with a complete IRONMAN ‘look’? | El Delta venue exceeds 5150 transition requirements (typical 5150 footprint ~80m × 25m vs. 70.3's 130m × 35m). The El Delta alliance commits the venue to deliver finish line, VIP, audio and venue adaptation to IRONMAN standards across both events of the year. Final dimensions TBC.
| 3 | Sound/Announcing - is it easy to relay information to athletes via sound/announcing within the area? | Yes. The El Delta partnership explicitly commits to production of a complete audio system, sound, announcing and event-route audio production.
| 4 | Are the entrances and egresses for the various legs, wide and accessible? Safe for athletes, volunteers and spectators? Obvious flows for race and other functions (Bike Check-in and out). | Designed for safety and clear flow, with Bike In/Bike Out clearly marked. Final layout TBC pending venue master plan.
| 5 | What access do spectators have to see transition zone/zones? | Spectator access integrated into the El Delta master-planned venue. Pedestrian flow controlled by volunteers and police. Specific layout TBC.
| 6 | What is our ability to work at transitions, (i.e., park trailers, drive forklifts and vehicles, etc.)? | Yes — El Delta is an active premium development with full infrastructure for heavy equipment access during setup and teardown.
| 7 | Where is proposed medical, athlete food, volunteer food, etc. located in relation to transition zone/zones? | Specific layout TBC pending venue master plan. Will follow IRONMAN standards for proximity. El Delta commits the venue to deliver venue adaptation per IRONMAN requirements.
| 8 | Is power accessible? | Yes — El Delta venue is built with premium modern utility infrastructure. Generator backup will be procured to ensure reliability.
| 9 | Sound/Announcing - is it easy to relay information to athletes via sound/announcing within the area? | Yes.
Finish Line | 1 | Does the Finish Line location have the ‘wow’ factor, showing off community and/or offer a unique finish? | Significant 'wow' factor upgrade vs. Encarnación. El Delta Nueva Asunción is positioning as the most ambitious premium real estate development in Paraguay — the venue offers an iconic finish line backdrop integrated with master-planned premium architecture. The finish line structure, arch, lighting, production and assembly are committed by El Delta under Bloque 1 of the alliance proposal — to be produced to international IRONMAN standards.
| 2 | Is there enough space at proposed location to fulfil all needed finish line functions (i.e., medals, hats, T-shirts, bleachers, media needs, announcers, medical, etc.)? | Yes. El Delta master plan provides ample space for all finish line functions — comfortably exceeding 5150 requirements (same finish line infrastructure serves both events across the year). Final dimensions TBC.
| 3 | When can the finish line area set up begin? Is there access for heavy equipment to do set up as required? Are there any restrictions? How long can you have access to tear down finish area? | No time restrictions anticipated. As Sede Oficial and partner, El Delta has direct authority over setup/teardown windows at the venue. Full access for heavy equipment is built into the development infrastructure.
| 4 | Noise - any noise restrictions with sound/announcing, etc.? | No noise restrictions — El Delta venue is master-planned for events. Location is designed to avoid impact on residential areas.
| 5 | What impact does location have on general public and are there restrictions? Any possible conflicts with community needs that can be averted? | Minimal public impact — venue is a controlled premium development designed for events.
| 6 | Medical - is there good access to medical tent and/or Emergency Management Services to access hospitals? | Direct access to Asunción hospital network: Hospital Central IPS, Hospital del Trauma, Sanatorio de la Costa. IRONMAN medical protocol followed at the finish line zone.
| 7 | Where is medical, athlete food, volunteer food, etc. located in relation to finish line? | Layout designed to enable efficient post-finish athlete flow with medical, food, hospitality and athlete services in proximity per IRONMAN standards.
| 8 | Is there access to good power, internet or does it need to be brought in? | Yes — premium modern utility infrastructure at El Delta provides reliable power and internet. Backup systems will be procured.
Additional Technical Functions/Areas | 1 | Is a warehousing location close to venues available? Is it a parking lot or secure warehouse location? Is it secure? Does it have a loading dock? Can trailers / equipment be stored in advance or post-race? | Warehousing options: (a) on-site secure space within El Delta venue, (b) our own trucks, (c) permanent warehouse in Asunción 20 minutes from the race venue. Equipment reuse between 5150 (April) and 70.3 (August) provides operational efficiency.
| 2 | Medical - Is there a potential medical partner? Access to Emergency Management Services / Ambulance? Is there access to significant trained medical personnel in the area? | Multiple premium medical partner options in Asunción: Sanatorio Italiano, Sanatorio San Roque, Hospital Central IPS, Hospital del Trauma (national reference), plus several specialized centers. Significantly broader medical network than Encarnación.
| 3 | Can tents be staked at various locations for safety? | Yes.
| 4 | Is there ample housing/accommodation for athletes close to venues? | Asunción offers >15,000 hotel rooms across all categories, including premium international brands. For the 5150 cap (1,000-1,500), accommodation capacity is more than sufficient and accessible across price points — well below saturation thresholds.
| 5 | Bussing/Parking - is it required and accessible? | Bussing is not strictly required — Asunción has stronger metropolitan transport infrastructure than Encarnación. Shuttle services from key athlete accommodation hubs to the El Delta venue will be evaluated to improve athlete experience.
| 6 | Weather/Other Environmental Factors
| 7 | What is the historical weather like the time of year proposed? What are the air and water temperatures, humidity, wind, potential rain (particularly thunderstorms)? | Asunción on April 25 (Southern Hemisphere autumn transition): average temperatures 18-27°C (64°F-81°F). Moderate humidity. Low rainfall risk (~80mm monthly avg, declining toward end of April). Comfortable race conditions — warmer than the August 70.3 slot but within IRONMAN comfort range for the Olympic distance. Start time will be optimized to leverage cooler morning conditions.
| 8 | Any other odd weather type occurrences that happen on a regular basis? | No.
| 9 | Altitude - how high is the location proposed? | Approximately 43 m above sea level.
| 10 | Any issues with pollution, air or water quality, or other environmental factors to be aware of? | No significant concerns identified. Asunción has adequate environmental conditions for international sporting events (recently hosted ODESUR South American Games).
Intangibles | 1 | Are there any ancillary benefits to being in this community (i.e., name brand communities, ties to triathlon, ties to other sporting events of interest, resort community, etc.)? | Yes — significant ancillary benefits. Asunción is the capital, economic and cultural center of Paraguay. Marca País Paraguay endorsement granted at national level, positioning the event as an official vehicle of Paraguay's international representation. The El Delta venue partnership embeds the event in the most ambitious premium real estate development in the country. Asunción has been actively positioning as international sporting events destination (ODESUR, World Rally Tour 2025, regional football tournaments).
| 2 | Is there strategic value to this location? | Major strategic value. (a) Capital city access — direct reach to the country's largest economic base and population center. (b) Silvio Pettirossi International Airport — direct flights to Miami, Sao Paulo, Buenos Aires, Lima, Santiago, with onward connections to Europe and US. Enables international athlete recruitment in a way Encarnación cannot. (c) El Delta Nueva Asunción as a master-planned premium development is itself a strategic asset for IRONMAN brand positioning, with strong audience overlap between IRONMAN 70.3 athletes and premium real estate buyers.
| 3 | Does this venue enhance the IRONMAN brand? | Yes — materially enhances the IRONMAN brand. The 5150 Asunción establishes the season-opener and feeder race for the IRONMAN 70.3 Paraguay 2027, creating a unified IRONMAN portfolio in Paraguay across two editions per year. Combined with capital-city positioning, premium master-planned venue (El Delta), SENATUR Marca País Paraguay endorsement, and broader sponsor/media pool, this strengthens IRONMAN's brand footprint in South America. The 5150 also serves as a development pathway to 70.3 participation.
| 4 | Sales opportunities
| 5 | Are there any unique sale or sponsorship opportunities to this venue? | Yes. Title sponsor ueno bank already secured for the event. Major sponsor under negotiation: El Delta Nueva Asunción as Sede Oficial + Sponsor Oficial under a multi-year framework 2027/2028 with option 2029.
| 6 | Are there companies headquartered in the area that provide you with a unique opportunity to use these companies as sponsors, medical providers, VIK, etc.? | Yes — significantly more than Encarnación. Most major Paraguayan corporates are HQ'd in Asunción: Ueno Bank, Itaú Paraguay, Banco Continental, Banco GNB, Tigo, Personal, Claro, Cervepar/Heineken, Grupo Vierci, Grupo Zuccolillo, plus premium real estate, automotive, premium hotel and consumer goods sectors. Asunción concentrates the country's purchasing power.
| 7 | Ancillary Functions (Expo/Banquets/Village/Housing/Bussing) | Expo, registration and ancillary functions will be hosted at the El Delta Nueva Asunción venue itself, integrated with the master-planned premium infrastructure. Specific layout TBC pending master plan.
| 8 | Expo - Is the location inside or outside? If outside is it in any way weather protected (particularly wind)? Is the space large enough (inside or outside) to host all areas of need (athlete check-in, merchandise, vendor and partner space)? | Both indoor and outdoor options available at the El Delta venue. The master-planned premium development is designed with flexible event spaces including weather-protected zones. Final configuration TBC.
| 9 | How close to the race venue is expo location? Is parking an issue? | Expo will be integrated with the race venue at El Delta.
| 10 | Is there power and internet at the proposed location? | Yes — premium modern utility infrastructure at El Delta provides reliable power and internet at the proposed expo location.
| 11 | What is the proposed model/location for the Welcome and/or Awards Banquet/Function? Traditional sit down with show? Community based (i.e. eat in the community) with show at a specific time. | Yes integrated to the venue
| 12 | How close is location to other race venues (transition/finish and expo)? | All race venues (transition, finish line, expo) will be integrated within the El Delta master-planned venue — substantially more compact than the Encarnación setup. Final distances TBC.
| 13 | Welcome Function / Awards Banquet or Functions - is there a facility that can hold banquet, or is a ‘circus’ tent required? How big of a tent can be procured? Can open seating be an option? | Yes — multiple options. (a) On-site within El Delta venue (premium hospitality facilities). (b) Premium hotels in Asunción (Sheraton, Crowne Plaza, Yacht & Golf Club Paraguayo). (c) Country clubs and convention centers in Asunción metropolitan area. Final venue TBC.
| 14 | Caterer - Is there a caterer to handle volume? | Yes. Asunción has an extensive premium catering market with track record in international events.
| 15 | Will/can Expo be open on race day? Day after? What is plan for Awards Function/Banquet? | Yes — expo can be open on race day and day after. Banquet on registration day under evaluation.
| 16 | Is there an ability to connect the merchandise tent to athlete check-in? | Yes.
Community/ Political (community monies/hotels/other streams) | 1 | Who is the local government, council or community? Do they have the ability to approve the necessary permissions to host the event, included but not limited to permits for swim, bike, run, finish line and all necessary area? | Local government: Municipalidad de Asunción (Intendente). National-level institutional support via Marca País Paraguay endorsement, Sports Secretariat of Paraguay, Tourism Ministry. Coordination protocol for full permitting (swim, bike, run, finish line, signage, accreditations) being established as part of this venue change application.
| 2 | Are there any jurisdictional issues that may cause problems (multi county, multi-state or sovereign areas)? Federal lands that require special permitting? | No multi-jurisdiction issues anticipated within the El Delta venue itself. Bike route segments that extend outside the venue may touch neighboring municipalities — manageable via standard coordination. No federal lands involved.
| 3 | Are permits year to year or can they safely be assumed to be for length of term of contract? | Permit term to be confirmed in upcoming meetings with Municipalidad de Asunción. SENATUR - Marca País Paraguay endorsement provides multi-year national-level backing. Multi-year permit structure will be negotiated to align with the multi-year partnership with El Delta (2027/2028 + option 2029).
| 4 | How stable is local partner/government? Any potential roadblocks from a political level? | Stable. Asunción municipality has actively positioned the city as international event destination. Marca País Paraguay endorsement is a national-level commitment that transcends municipal political cycles.
| 5 | Can contracts be enforced? | Yes — full legal validity under Paraguayan civil and commercial law.
| 6 | Is community versed in large scale sporting events? | Yes — Asunción has hosted multiple major international sporting events: ODESUR South American Games (2022), World Rally Tour Paraguay 2025, regional football tournaments (Conmebol), multiple international marathons and running events.
| 7 | Are there safety concerns relative to the locale? | No significant safety concerns. Asunción is the safest major metropolitan area in Paraguay.
| 8 | Other risks / barriers to the event? | Primary residual risk: this venue change requires re-pacting of the existing license with WTC/IRONMAN Group and re-confirmation of permits structure with new jurisdictional counterparties. This questionnaire is part of that re-pact process.
Personnel | 1 | How is the event to be staffed? Is there a potential local race director and/or staff? | Core Rebelocity team from Encarnación 2025/2026 transfers to Asunción setup.
| 2 | How is the event to be staffed? Is there a potential local race director and/or staff? | Strong volunteer base from prior events.
| 3 | How does the event fit in the calendar of duties for full-time operational staff? (Europe/Asia)? | Proposed race date: SUNDAY APRIL 25, 2027 — Southern Hemisphere autumn transition. Strategic positioning: (a) season opener for the regional Southern Cone triathlon calendar, (b) build-up race for the IRONMAN 70.3 Paraguay 2027 (August 22, 2027 — 17 weeks later), providing an ideal training cycle for athletes pursuing both events as a coordinated season, (c) post-Easter window (Easter 2027 = March 28; April 25 is 4 weeks post-Easter), (d) clear of Paraguayan national holidays (Labor Day May 1, Independence Day May 15). Coordination with WTC to confirm slot. Subject to WTC approval.
| 4 | Athlete Assumptions | Event athlete cap target: (2027) target: 600 atletas. Growth trajectory enabled by capital-city access + international airport connectivity. The 5150 format is positioned as season-opener and feeder race for the 70.3. Conservative downside: 400 atletas in Year 1, mature target 1,000 by Year 3.
| 5 | Where will you source athletes from? | Source markets: Paraguay (substantially broader reach from capital location), Argentina (Buenos Aires direct flights), Brazil (Sao Paulo + onward), Uruguay, Chile, Bolivia, Peru. The 5150 distance has stronger appeal to the regional Olympic-distance triathlon base than the 70.3, opening recruitment to a different athlete profile (younger, season-builder, multi-discipline crossover).
| 6 | What is the risk of cannibalization? What races will be affected? | Minimal cannibalization risk. The 5150 Asunción is positioned as season-opener and 70.3 build-up race within the Rebelocity Paraguay portfolio. The 5150 (April) and 70.3 (August) target the same athlete base at different points of the training cycle — complementary, not cannibalizing. Local Paraguayan triathlon market is underserved at the Olympic distance.
| 7 | Competing races in the vicinity? | No significant competing races have been identified in the proposed April 25, 2027 window. April is a transition month in the regional triathlon calendar — Southern Hemisphere autumn quietly opens after summer racing season, allowing Asunción to be positioned as a season-opener for the regional Southern Cone triathlon calendar. That said, it is important to note that calendar protection within the region is highly relevant. In 2026, IRONMAN 70.3 Buenos Aires directly affected our event when it was later positioned only one week before our established race date, which had already been in place since the previous year. This overlap creates a direct impact, as both events depend on a very similar regional athlete market. For this reason, we believe the proposed 2027 window should be evaluated not only based on the absence of current conflicts, but also with a clear commitment to regional calendar coordination and protection.
Note on D9: TBC — pendiente master plan El Delta, ruta final, o confirmación institucional.
Note on D10: TBC — pendiente master plan El Delta, ruta final, o confirmación institucional.
Note on D12: TBC — pendiente master plan El Delta, ruta final, o confirmación institucional.
Note on D13: TBC — pendiente master plan El Delta, ruta final, o confirmación institucional.
Note on D15: TBC — pendiente master plan El Delta, ruta final, o confirmación institucional.
Note on D16: TBC — pendiente master plan El Delta, ruta final, o confirmación institucional.
Note on D17: TBC — pendiente master plan El Delta, ruta final, o confirmación institucional.
Note on D20: TBC — pendiente master plan El Delta, ruta final, o confirmación institucional.
Note on D22: TBC — pendiente master plan El Delta, ruta final, o confirmación institucional.
Note on D24: TBC — pendiente master plan El Delta, ruta final, o confirmación institucional.
Note on D26: TBC — pendiente master plan El Delta, ruta final, o confirmación institucional.
Note on D27: TBC — pendiente master plan El Delta, ruta final, o confirmación institucional.
Note on D28: TBC — pendiente master plan El Delta, ruta final, o confirmación institucional.
Note on D32: TBC — pendiente master plan El Delta, ruta final, o confirmación institucional.
Note on D33: TBC — pendiente master plan El Delta, ruta final, o confirmación institucional.
Note on D34: TBC — pendiente master plan El Delta, ruta final, o confirmación institucional.
Note on D36: TBC — pendiente master plan El Delta, ruta final, o confirmación institucional.
Note on D38: TBC — pendiente master plan El Delta, ruta final, o confirmación institucional.
Note on D43: TBC — pendiente master plan El Delta, ruta final, o confirmación institucional.
Note on D44: TBC — pendiente master plan El Delta, ruta final, o confirmación institucional.
Note on D46: TBC — pendiente master plan El Delta, ruta final, o confirmación institucional.
Note on D47: TBC — pendiente master plan El Delta, ruta final, o confirmación institucional.
Note on D49: TBC — pendiente master plan El Delta, ruta final, o confirmación institucional.
Note on D54: TBC — pendiente master plan El Delta, ruta final, o confirmación institucional.
Note on D79: TBC — pendiente master plan El Delta, ruta final, o confirmación institucional.
Note on D80: TBC — pendiente master plan El Delta, ruta final, o confirmación institucional.
Note on D84: TBC — pendiente master plan El Delta, ruta final, o confirmación institucional.
Note on D85: TBC — pendiente master plan El Delta, ruta final, o confirmación institucional.
Note on D87: TBC — pendiente master plan El Delta, ruta final, o confirmación institucional.
Note on D90: TBC — pendiente master plan El Delta, ruta final, o confirmación institucional.
Note on D91: TBC — pendiente master plan El Delta, ruta final, o confirmación institucional.
Note on D92: TBC — pendiente master plan El Delta, ruta final, o confirmación institucional.